## Blad1
C(hris)/R(ichard)/B(oth) | Date | Time spend | Description | Think time | Development time | Experiment time | Analysis time | Write time | Wasted time
B | 2014-09-23 | 5 | General architecture of a cloud system | 10
B | 2014-09-24 | 6 | General architecture of a cloud system/trying to get OpenNebula to work | 6 |  |  |  |  | 6
B | 2014-10-01 | 6 | Researched the possibilities of working with OpenNebula Cloud | [5 empty] | 12
B | 2014-10-07 | 4 | Researched the possibilities of working with OpenNebula Cloud/Meeting with TA | 2 |  |  |  |  | 6
B | 2014-10-08 | 6 | Researched the possibilities of working with OpenNebula Cloud | [5 empty] | 12
B | 2014-10-14 | 6 | Decided to switch to EC2 | 6 | 6
R | 2014-10-15 | 6 | Image processing |  | 6
C | 2014-10-15 | 6 | Deamonizing |  | 6
R | 2014-10-21 | 3 | Image processing |  | 3
R | 2014-10-22 | 3 | Image processing |  | 3
R | 2014-10-23 | 6 | Building small setup for sending images of socket to be processed + experiments |  | 4 | 1 | 1
C | 2014-10-23 | 6 | Scripts for deamonizing |  | 6
C | 2014-10-24 | ??? | Scripts for deamonizing
R | 2014-10-28 | 6 | Multithreaded the workers + started on the emulator + report setup |  | 5 |  |  | 1
C | 2014-10-28 | 6 | Head node |  | 6
R | 2014-10-29 | 6 | Finished Emulator + recover from failure on GitHub + introduction report |  | 4 |  |  | 1 | 1
C | 2014-10-29 | 6 | Head node |  | 6
R | 2014-10-30 | 6 | Scheduler policies + cleanup work |  | 6
C | 2014-10-30 | 6 | Head node |  | 6
C | 2014-10-31 | ??? | ???
C | 2014-11-01 | ??? | ???
R | 2014-11-05 | 6 | Scheduler policies + emulator + background section report |  | 3 |  |  | 3
C | 2014-11-05 | 6 | Lease/release policy + head node |  | 6
R | 2014-11-06 | 6 | Bugfixes + schedulers + testing |  | 4 | 1 | 1
C | 2014-11-06 | 6 | Monitoring + testing |  | 4 | 1 | 1
R | 2014-11-07 | 6 | Report writing |  |  |  |  | 6
C | 2014-11-07 | 6 | Bugfixes + testing |  | 3 | 3
C | 2014-11-08 | ??? | ???
R | 2014-11-09 | ??? | Report writing
C | 2014-11-09 | ??? | ???
|  |  | Totals: | 24 | 87 | 6 | 3 | 11 | 37 | 168